Roles and Responsibilities among the Chair, Secretariat of ASOSAI WGEA, and Host SAI in ASOSAI WGEA Activities (draft)

First draft in October, 2016

Secretariat of ASOSAI WGEA

Pre Event

| Tasks | Chair | Secretariat | Host SAI |
| --- | --- | --- | --- |
| Topics for discussion |  |  |  |
| Propose the candidate topics for discussion, disseminate to member SAIs for consultation through questionnaire (if necessary) |  | X |  |
| Determine the topics | X |  |  |
| Notify the topics and other requirements in the invitation letter * Such requirements may include guideline for preparing country papers, timeline for submission (about one month before the meeting), time for presentation and PPT, etc. | X |  |  |
| Collect the country papers and PPT presentations from participating SAIs and participants |  | X |  |
| Print meeting materials, if necessary * Paper-less communication is encouraged at the meeting of ASOSAI WGEA |  |  | X |
| Programme |  |  |  |
| Propose the tentative programme in consultation with stakeholders |  | X | X |
| Preliminarily contact the invited guests, observers, and/or subject matter expert (if necessary) of intent for confirmation |  | X |  |
| Draft the tentative programme for approval |  | X | X |
| Approve the tentative programme | X |  |  |
| Administrative Issues |  |  |  |
| Determine the dates and venue (Please refer to “Annex1”) |  | X | X |
| Determine the hotel for accommodation |  | X | X |
| Make block reservations with the hotel for accommodation depending on the number of participants expected |  |  | X |
| Book meeting rooms * Preferably one large meeting room (approximately more than 200m2), one Secretariat room (approximately 50m2, with computers, printer, photocopier, internet access) |  |  | X |
| Determine the excursion programme |  | X | X |
| Send an invitation letter addressed to ASOSAI member SAIs and other necessary guests/observers, if any, notifying the general information about at least 4 months prior to the meeting * General information may include, for example, introduction, dates and venue, meeting program, registration form, hotel reservation, transportation services, contact information, etc. | X |  |  |
| Receive the registration information of the participants * Keep close communication between Secretariat and host SAI |  |  | X |
| Prepare letters of visa facilitation to those SAIs that are required to obtain visas for the host country if necessary |  |  | X |
| Deliver an orientation prior to the meeting, if necessary |  |  | X |
| Organize welcome reception (voluntary basis) |  |  | X |
| Meeting Logistics |  |  |  |
| Prepare a brief case/bag and information handbook/brochure * Inside the case/bag are meeting program, list of participants, contact details of liaison officers, stationery, souvenirs, badge, etc. * Necessary information in handbook/brochure may include meeting programme and agenda, excursion schedule, brief information of host country/city and excursion sites. |  |  | X |
| Arrange audio-visual aids, microphones, projector, screen, and other digital devices, stationery, place card, water, etc |  |  | X |
| Airport Welcome |  |  |  |
| Arrange airport welcome * Airport Protocol is recommended to provide to the VIP participants. * The host SAI may assign the liaison officers to each delegation of participating SAIs. |  |  | X |
| Provide transportation from airport to hotel |  |  | X |

During Event

| Tasks | Chair | Secretariat | Host SAI |
| --- | --- | --- | --- |
| Administrative Issues |  |  |  |
| Provide transportation between the hotel and the meeting venue, if necessary |  |  | X |
| Registration for the opening ceremony |  | X | X |
| Arrange the facilities for simultaneous interpretation of various languages, if requested. |  |  | X |
| Organize opening ceremony * Some host SAI may assign an emcee for the opening ceremony. |  | X | X |
| Preside over the meeting and discussion * Some host SAI may assign an emcee for the meeting. * The Chair can authorize the Secretary General, the head of the Secretariat, to moderate the meeting. * During the session of presentation and discussion at the seminar, the Chair/Secretary General may ask the selected participants as the moderator for the individual topic to help run the seminar. * The host SAI may award the gifts/souvenir to the presenters on voluntary basis. | X | X | X |
| Arrange group photo session for all the participants Distribute the group photo to the participants Take photos of participants during the meeting and other activities |  |  | X |
| Record during the meeting and draft the minutes * Host SAI may prepare audio-video facilities to record the whole meeting if needed. |  | X | X |
| Arrange additional digital devices and stationery, if requested |  |  | X |
| Print additional materials, if requested |  |  | X |
| Provide working lunches of international meals during the meeting for all participants * The working lunches is preferably provided in the form of buffet. |  |  | X |
| Prepare tea/coffee with snacks for break |  |  | X |
| Provide a welcome or farewell dinner for all participants * Welcome or farewell dinner will be normally hosted by AG/DAG of host SAI on voluntary basis, even it is a general practice. * Invitation card to dinner should be given to all participants in advance. |  |  | X |
| Host an official dinner for all participants * The official dinner will be normally hosted by the Chair of ASOSAI WGEA or his representative. * Invitation card to dinner should be given to all participants in advance. | X | X |  |
| Provide meeting rooms for a smaller group at the request of the participants, if necessary |  |  | X |
| Coordinate and provide local transportations, if necessary |  |  | X |
| Arrange return flight confirmation and airport transportation |  | X | X |
| Prepare a CD/USB containing the meeting materials and photos and distribute to the participants |  |  | X |
| Prepare the evaluation form to the participants and collect back |  | X | X |
| Excursion and Cultural Programs |  |  |  |
| Arrange excursion program |  |  | X |
| Provide transportation between the hotel and excursion site |  |  | X |
| Provide lunch on the day of excursion |  |  | X |
| Take photos of the participants |  |  | X |
| Arrange a doctor for medical emergencies (if available) |  |  | X |
| Arrange a separate program for accompanying persons, If necessary |  |  | X |

Post Event

| Tasks | Chair | Secretariat | Host SAI |
| --- | --- | --- | --- |
| Airport See-off |  |  |  |
| Arrange airport see-off to the participants * Airport Protocol is recommended to provide to the VIP participants. * The host SAI may assign the liaison officers to participants. |  |  | X |
| Provide transportation from hotel to airport |  |  | X |
| Administrative Issues |  |  |  |
| Prepare appreciation letters for the Host SAI, invited guests, and the participating SAIs | X | X |  |
| Develop the news of the meeting to INTOSAI WGEA, ASOSAI, and other stakeholders |  | X |  |
| Prepare the meeting minutes and asking the participants for corrections |  | X |  |
| Approve the minutes of the meeting | X |  |  |
| Upload brief summary, meeting materials, minutes and photos on the website of ASOSAI WGEA |  | X |  |
| Prepare and print the collections of country papers/audit cases if necessary |  | X |  |
| Report the activities of ASOSAI WGEA to Governing Board meeting and Assembly of ASOSAI, Steering committee meeting and Assembly of INTOSAI WGEA, and other occasions | X |  |  |

Note:

- “Event” comprises the biennial Seminar on Environmental Audit and working meeting of ASOSAI WGEA.

- Despite the roles and responsibilities shown above, close consultation among the Chair, the Secretariat of ASOSAI WGEA and Host SAI are encouraged if necessary.

- The roles and responsibilities shown above are subject to change.